| Krowji Phase 2 - Project programme |  |
| --- | --- |
| Formal start date for ERDF purposes (date from which eligible expenditure may be incurred) | 4th May 2018 |
| Financial completion date for ERDF purposes (date by which eligible costs will have been defrayed) | 30th September 2020 |
| Key milestones |  |
| Project Management and Design Team tender | September to October 2018 |
| Cornwall Council funding decision | 31st October 2018 |
| Arts Council England funding decision | 31st October 2018 |
| ERDF funding decision | Late 2018 |
| Post-award project mobilisation | January 2019 |
| Detailed Design | January to March 2019 |
| Main contractor tender process | May to August 2019 |
| Hand over site to contractors | September 2019 |
| Completion and handover to Client | April 2020 |
| Comments |  |
| The key controlling factors here are the funding awards – if any of the three applications are unsuccessful then the project will probably not be able to proceed. Apart from that, most steps should be straightforward – the project has full detailed planning approval, the Client owns all the land and the project is not dependent on any other consents. |  |